## Key Details for Proposal To Pri
Scroll down to see all of information here Title For Career Fair * For example: Trade Up! Build Your Future and Make Your Career Connections Invite * College and University Departments, Trade Associations/Unions, Private Schools, Employers, Your Coop Students, Board OYAP and Dual Credit Contacts, etc. For * Grade 9 - 12 students; Grade 7 and 8’s from Feeder Schools * Any other school or specific classes from schools - Capacity depending * Building your co-op program * Final cumulative assignment for your co-op students Funding * Your Principal and/or Contact Board OYAP and COOP Board Consultant For Money to Support Fair to help cover costs such as: * Buses for grade 7 and 8’s from feeder schools * Luncheon and Thank You's for Invited Guests * Buttons for Guests and Student Leader/Helpers * OYAP or Trade Up Made T-Shirts Duration * School Day Start Time and end 30 minutes before the end of the day for take down Time of Year Fall - End of November if possible - before December College and University Exams Spring - Early or Mid May after college and university exams Some Important Logistics * Call your school grades down by period...i.e. Grade 10's first period; Grade 12's second period; Grade 9's third period; Grade 11's last period of the day * If you have two entrances to the gym....to control traffic flow...suggest all upstair classes use one entrance and leave by that entrance and all downstair classes enter and leave by the other entrance to the gym * If inviting feeder schools, consider their school start and finish times to schedule their arrival and departure time...again to control traffic in gym * For health and safety reasons, you can not block any gym doors leading outside..leave a reasonable open space for emergency exits of gym outside

## Key Planning Steps
Steps | Suggested Step Descriptors
Determine Date | If fall - end of November best for Colleges and Universities before exams If Spring - Mid to Late May after exams
Introduce Career Fair Event to Your Coop Students - First Integration Day | Show students examples of student displays from previous years, if applicable
Consider Location in School Consider electrical logistical needs - number of outlets | If Gym - clear date with Department Head first unless Principal has more sway over getting Physed to agree Book with Community Use of Schools so you can set up the evening before and have extra time after school the next day for take down
Arrange to meet with Principal to Get Approval
Order Tables From School Board | Speak to head custodian or person responsible for ordering tables from school board. Build a good relationship with the school Head Custodian Obtain measurements of gym; determine size of long tables to be used; and estimate number of tables to fill gym - estimate on the higher end to ensure you have enough Have tables arrive the day before and picked up the morning after the Fair I ordered 44 tables (2 by 6 feet I believe) Sample of my GYM Layout
Create a Spreadsheet of Guest Contacts | Visit local College and University websites Speak to your Student Services/Guidance to find out if there is a main point of contact within college or university who reach out to individual departments to participate in such activities. Create a list of departments and name of department contacts and their contact information/emails/phone Identify those you wish to attend your fair - vary it up from college and universities to represent several areas of interest for all students See if you can create letter for main college/university contact to send out to departments - might be a better sell. Visit Local Trade Association/Union Websites and/or contact board OYAP peson who may have list of contacts Brainstorm local private schools - i.e. Cordon Bleu, Fashion Academies, Airports and Flying Schools Brainstorm small and large employers in need of future employees - i.e. Trade related, Travel and Tourism Industry, Government (i.e. Military), Music Industries Sample worksheet
Begin Reaching out To Potential Guests | Create standard letter and send out emails tailoring letter where appropriate Use spreadsheet to record results and for follow up
As Guests Respond - Send out/Share Guest Particulars Info | As guests respond use spreadsheet to keep track of needs, numbers, and times on your master guest google sheet
Reach out to Feeder Schools | Feeder School Letter Feeder School Response Sheet Feeder School Field Trip Form Emails to confirm bus bookings and timings Create Scavengar Hunt Activity For Feeder Schools and Home School Teachers - Note - divide questions into type categories (A, B, C) as they are not all applicable to all guests. Then place Letter on each guest table so studnets can identify from which category of questions to ask. Determine number of student helpers to help
Arrange Luncheon For Guests | Determine caterer - school foods class or local business Determine numbers and budget How much lead time Determine number of student helpers (not coop students) to help with set up and take down.
Student Leaders/Helpers Throughout The Day Send out email to teachers of leadership or link leader classes or extra curricular groups you would like to approach to help with execution of Fair. | Tasks such as: Greeting guests as they arrive and escorting them to gym; answering quesitons they may have; greeting feeder schools and escorting and staying with them in gym; floaters in gym throughout the day to assist guests or student attendees with questions (i.e where is the washroom...etc) Escorting Guests to and from Luncheon Ensure feeder school students do not leave gym unattended by a student helper or teacher to escort to the bathroom etc. Help with take down and clean up Help with set up of Luncheon and helping when Guests Arrive to Eat and Clean UP Remember to send out final list of students who will be helping and out of class 2-4 days in advance. Prepare Responsibility Lists with Student Helpers
Send out emails to entire school staff regarding upcoming Career Fair. | First one 3-4 weeks in advance - teaser and to help them plan in advance of it Second one - 2 weeks in advance to remind them to plan for it Final or 1 week prior to Fair Day before - day or two before event
Promotions | Money for Buttons for Coop Students, Guests and Student Helpers T-Shirts for Student Helpers Banner of Theme upon Entrance of School Posters around Schools
Signage | Signs with names of Guests attached to tables in gym Signs showing where bathrooms for guests
Thank Yous | Have student(s) prepare Thank You cards and distribute to guests day of Fair Thank you email to all staff who helped out and/or gave up their clasroom for the day, custodians, main office staff, etc.
Other | Place bottles of water on guest tables the night before as well as some chairs behind tables for those that may need to sit (i.e. pregnant guests)
Logistics | Create visual of where guests and coop students will set up and provide signage on tables the night before Have student go around and provide wifi sign in to guests Be sure to collect enough extension cords and power outlets and strategically plan out where guests will set up based on needs - Borrow extension cords, multipower outlets, etc... Fire Hazard - Leave big enough space near gym doors to exit if gym leads to the outside the building Consider - Mosts guest table around perimeter of gym; coop students displays on the inside but allow for multiple walking pathways on the inside where student displays are to manage l traffic